## Khalili
ActivityLogin | getError | Display error message
ActivityUserProfileEdit | Design | there is no any fields for sex and email confirmation status
ActivityUserProfileEdit | changePassword changeBirthdate |  | view fault
ActivityUserProfileEdit | save | sex
ActivityNewBusiness_Step1 | onCreate | what is TODO: after loading category
ActivityNewBusiness_Step1 | showChooseCategoryDialog | what is this for?
PassingBusiness | setValue | Wrong
ActivityNewBusiness_Step2 | updateViews
ActivityNewBusiness_Step2 | submit | TODO it goes back to the ActivityNewBusiness_Step1
ActivityNewBusiness_Step2 | Design | where is hashtag list?
Where is delete business option
HomePostsAdapter | showDeletePopup() | where is business.id and post.id?
PostAdapter | showOptionsPopup() | where is business.id and post.id?
FragmentHome | getResult() and getError()
FragmentProfile | getResult() and getError()
ActivityNewPost | submit | add business.id and hashtag list
RequestUserConfirmation |  | there is no option to request user email confirmation
FragmentBusinesses | getResult() and getError()
ActivitySetting | getResult() and getError()
How did you implement lazy load in post adapter?
FragmentFollowers | getResult() and getError()
FragmentSerach | getResult() and getError()
FragmentSerach | setUpCategoriesFitler()
FragmentResult | onCreateView() getResult() and getError()
FragmentResultUser | onCreateView() getResult() and getError()
FragmentReviews | onCreate() onCreateView() getResult() and getError() sendReview() loadMoreData()
FragmentUserReviews | getResult() and getError()
There is no option to see blocked user list in business profile page
There is no option to send friend request
FragmentFriends | onCreateView getResult() getError()
FragmentRequests | onCreateView getResult() getError()
Dialogs.showMessages() | in ActivityLogin doesn't work
going from login activity to profile fragment is too slow
RegisterBusiness | address hashtag List
EditBusinessProfile | it doesn't go in edit mode isEditing is false
DeleteBusiness | business object is null
going from login activity to profile fragment is realy toooooooooo slow, something about 10 seconds
close deleteBusiness dialog after delete
ActivityBusinessSetting | getResult() and getError()
inserting hashtag doesn't work proerly in addPost
ActivityNewPost_Step2 | submit()
ActivityNewPost_Step1 | click on next without choosing picture
Request user confirmation
FragmentFollowers | onCreate()
FragmentResutl | executing SearchBusinessLocation() is too long
entering fargmentProfile | GetUserHomeInfo: get visitor and visited user id
business profile picture | register business
Register Business | display error message
Register Business | after getting error, when I click on register new business, PassingBusiness.getValue will fire and FORCE CLOSe
Map
Register Business | after adding register business, new business must be added to the list. User should'nt go to the last page before finishing webservice
FragmentProfile | myOwnBusiness: myOwnBusiness
ActivityBusienssSetting | TODO
update business profile info | user shouldn't be able to insert new businessUserName
validate price field in add post
FragmentProfile | profileId? Where you initialize it?
FragmentProfile | diplay user info
change adapters to user DownloadImages class to download image
ActivitySetting | onCreate
FragmentProfile | TODO: assignNow
FragmentProfile | 169
FragmentSearch | setUpSuggestions: fill with real data ( اطلاعات چه هستند؟ حضورأ با آقای ریحانی صحبت میکنم ) | probably will implement in phase2
FragmentResult | lazy load implementation ( اطلاعات تودو شد لطفأ مشاهده کنید ) | Done. Check the code
SearchBusinessByLocation | display distance display business profile picture
FragmentResultUser | lazy load implementation ( اطلاعات تودو شد لطفأ مشاهده کنید ) | Do like FragmentResult
Display reviews | display picture
ReviewBusiness | business' owner shouldn't be able to review his own business
FragmentResult | getResult (lotfan grid adapters result ro bebinid, todo gozashtam ) | ?
Download pictures in all adapters
EditeReview | ForceClose
EditeReview | close popup after action update review list after upate and delete
like post | post can't be liked by post's owner. Check owner of post نیازمند داشتن یوزر آیدی شخص قرار دهنده ی پست هستیم if post liked by user, the user shouldn't be able to like it again. Check post.isLiked این مسأله در سمت وب سرویس قبل از ثبت لایک بررسی میگردد | Post object has a field named "isLiked". It determine current user liked the post or not. If "isLiked" equals "True", the user shouldn't be able to like. It means like button onClickListener do nothing. If "isLiked" equals "False", the user can like the post. After liking, the value of "isLiked" in mentioned post object should change to "True" in array list.
implement deleteReview, likePost, commentPost, reportPost, deleteComment, blockUser ,unblockUser ,getBlockedUsers, requestFriendShip answerRequestFriendShip rateBusiness(review without text) | تمامی موارد درون آداپتر ها و فایل DIALOGS قابل ردیابی و پیاده سازی هستند. با پیاده سازی وب سرویس ها notify ها را نیز اضافه خواهم کرد.
FragmentFriends | getResult: doesn't show the result
FragmentSearchResult | list scroll: FORCE CLOSE
FragmentProfile | implement getTimeLinePosts(wall posts)
wall adapter | change adapter to display wall posts properly
2015-01-10
register business | get time picker is slow
register business | after adding new business, business listview doesn't update | Done
ProgressDialog | disable dialog with back | FragmentProfile
EditUserProfile | don't display null if string is empty
EditUserProfile | there is no way to change email
Remove all test parts
GetBusinessHomeInfo | user profilePictureId not profilePicture
GetBusinessHomeInfo | display coverPicture with a permanent picture
Update business profile info | remove businessUserName field. | Done
Update business profile info | Assign business info in update business profile info in getResult | business' about isn't displayed
Close all dialogs in getError() |  | tested just in getBusinessHomeInfo
Update business profile info | set business category and subcategory base on business profile info | couldn't test because of GetBusinessProfileInfo error
Update user profile Info | set user sex base on user profile info | couldn't test because of GetBusinessProfileInfo error
Update user profile Info: dialog birthdate | fill year, month and day edittext with user birthday info
Update user profile Info | change profile picutre in profile fragment after updating | Done
GetBusinessProfileInfo | assign business info | couldn't test because of GetBusinessProfileInfo error
2015-02-10
EditUserProfile | close change email dialog after submit and displaying second dialog | Done
EditUserProfile | close change password dialog after submit and displaying second dialog | Done
2015-02-14
ActivityNewBusiness_Step1 | getError->Dialogs.showMessage : throws exception | Done
FragmentProfile | how do you display description for business? | Done
ActivityNewBusiness_Step1 | disable businessUserName checking in editing mode | Done
ActivityNewBusiness_Step2 | disable webservice progress dialog on back pressed | Done
ProfileFragment | getResutl->assignNow: line 549 throws exception | Done
ActivityNewBusiness_Step1 | throws exception: backing from ActivityNewBusiness_Step2 and clicking on the description edtitext
ProfileFragment | don't display hashtags in description field | Done
ActivityWorkTime | returns wrong times | Done
ProfileFragment | display profile picture | Webservice bug
ActivityNewBusiness_Step2 | display success message and back
ActivityNewPost_step2 | remove waste dialog | dialog is displayed after entering activity
2015-02-15
ActivityBusinessSetting | force close after removing business | force close occures in ActivityMaing->backToRoot->onBackPressed line 305
ActivityNewPost_step2 | there is an option to choose picture, why?! | Done
ActivityNewPost_step2 | isEditing is true while adding new post
ActivityNewBusiness_Step1 | throws exception like No 121
ActivityNewPost_step2 | getResult: force close
FragmentProfile | post are not displayed!!! | Done
PostAdapter | listview has lag | Done
| user hasn't right to edit shared post | Done
| share and report couldn't be displayed | Done
| share option didn't implement | Done
ActivityNewPost_step1 | post picture is not displayed | Done
ActivityNewPost_step2 | change getResult
2015-02-16
OptionPost | Line 101: don't you think you must remove test part and replace post.id and post.businessId with test values? You wrote an answer for me?!!!!!!!!!!
FragmentBusinesses | getResult: webservice works finde but getResult doesn't display businesses in listview
ActivitySetting | change message in getResult and back to the previous page and execute GetUserHomeInfo againt to update permissions
PostAdapter | take creation date as int(for the test, pass an integer value)
display businessUserName and business profilePicture you have businessUserName and businessProfilePictureId in GetBusinessHomeInfo webservice(getResult when result is instance of Business)
Display right vaules for like number,comment number and share number
2015-02-17
Update user profile | change birthdate dialog to return month as 2digit string like 1392/02/12
ActivityUserProfileEdit | display user profile picture with profilePictureId and using DownloadImages class
ActivityNewBusiness_Step2 | Add website field
FragmentCallInfo,FragmentNewBusiness_step2 | display map in appropriate zoom scale
ActivityNewBusiness_Step1 | Update mode: display business profilePicture(with profilePicture and not with profilePicutureId,I will do that later) and businessUserName
UpdateMode: spinners display wrong values (for the test,choose a business with category:cloth and subcategory:men cloth) ( check again please )
ActivityNewBusiness_step2 | Update mode: display business existed info in related fields
ActivityNewPost_Step2 | Force close after adding new post or updating post in getResult
You should add new added post to the adapter in previous page
FragmentProfile | Display businessProfilePicture and businessUserName and post title in business' posts gridAdapter ( what do you mean exactly ? Shouldn't we show picture only ? )
All views which execute webservices must have progressBar dialog | GetBusinessHomeInfo,GetBusinessPosts don't have this dialog
FragmentProfile | Follow request button wouldn't change after FollowBusiness execution ( I've got an error from web service when I touched follow, please check that, i 'll check this too)
How do you display DeletePost success message?
PostAdapter | creationDate is in int format now, make necessary changes Attention: newest post should be displayed first ( they're sorted by id from webservice I think, am I wrong ? )
2015-02-18
implement unlike post | there is unlike webservice
implement unfollow business | will be done……
implement unfriend user | will be done……
Implement Get all comment notifications webservice | Create a feature in User home page or elsewhere to display user's all comment notifications. This webservice returns last comments of user's all businesses. You have to create a listview with these items: user's profile picture (how wrote the comment) post's profile picture (which the comment belongs to) comment text with clicking on each item, the post will be displayed (with using post.id)
Update Review | there is no feature to update a review in Review page
Delete Review | there is no feature to delete a review in Review page | see options review please
ActivityComment | Force close: getResult
FragmentComment | some time it gets Force Close before executing doInBackground in sendComment webservice. Check it plz.
Force close: getResult (if webservice is executed)
2015-02-21
PostAdapter | ViewHolder -> initial() ->this.options.setOnClickListener : line 135
update list after deleting one post
ActivityNewBusiness_step1 | put progress dialog for chaging categroy spinner and executing GetSubcategories
ActivityNewBusiness_step1 | pass wrong business.id to the ActivityNewBusienss_step2. check ActivityNewBusienss_step2 line 166 to see worng id.
FragmentProfile | If user have 0 friend or review or followed business: Don't go to the related pages If business have 0 follower or review: Don't go to the related pages
2015-02-22 | 2015-02-22
HomeAdapter(I think) | FragmentProfile: when GetUserSharePost gets error, the user home info must be displayed or when GetBusienssPosts get error, the business home info should be displayed. Modify adapter to diplay only header when you get error in mentioned webservices
By clicking item in gridview mode, nothing happens! (It should display post info in seprate page)
Why GPS is always running?
It shouldn't be any blank page in the app. If any webservcies gets error, after displaying error message, with clicking on ok button in dialog, user should navigate to the previous page
Where did you call GetBlockedUsers? | by clicking on "مسدود شده ها" in FragmentFollower, GetBlockedUsers will not run | Done.
FragmentBlockeds | businessId is not passed correctly to the webservice | Done
Display result in listview, getResult: line 195
Implement RequestConfirmation in View layout | It is the second time I mention it! | will be done……
FragmentComment | Add sent comment to listview | Done by Khl
| Clear comment edittext after successfully executing SendComment webservice | Done by Khl
| update post comment number in adapter after successfully executing SendComment webservice | I'll talk with you about this
In unseen.xlsx file for " Comment on post" you said: «کامنت قرار میگیرد اما تعداد کامنت ها به درستی نمایش داده نمیشوند» | what did you mean?
Where did you call GetBlockedUsers?
Where did you call GetAllCommentNotifications? | It is the second time I mention it! | Kvh: It is done. Change the intent in AlarmReciever line 56. I tested with ActivityMain but I got Force Close!
FragmentProfile | Loadmore data for business' post when business has no more posts | What do you mean ? I've reimplemented it, please check if it's working right ??
How do you rate a business?!!! | there is no option in View layout
PostAdapter | ForceClose after successfully executing Like webservice
Implement Unlike | I get Undefined error when using unlike!!
ActivityLogin | getResult: line 148
ActivityMain | do not exit with onBackPressed
check itmes.size to execute loadMoreData
Dismiss all progressDialogs with onBackPress | It is the second time I mention it! | why? I think we've talked before and decided to make them un cancelable Kvh: I talke to Mr. Reyhani and He said all dialogs should be cancelable!
Dialogs | showCommentEditPopup: line 204: implement updateComment webservice | should be tested, if you can, test it please
2015-02-23
FragmentProfile: FollowBusiness | Display progress dialog while followBusiness webservice is executing
Change follow button to the green button after successfully webservice executing
There is no option to unfollow business in view
FragmentProfile: friendship status | Display progress dialog while requestFriendship webservice is executing
There is no option to unfriend in view
After requesting friend ship with a user, friendship status button shouldn't be green, because friendship status is REQUEST_SENT. After accepting the requested user, the status will be FRIEND and that time, the button should be green
Change all image size where you directly enter integer value. | use Image_M.getImageSize(Image_M.ImageSize.Large) for example
Delete comment | Display progress dialog while followBusiness webservice is executing
Update the comment list after deleting comment
You display showCommentDeletePopup instead of showCommentDeleteFromMyBusinessPopup when the business owner wants to delete a comment on one of his posts
FragmentFriends | getResutl: line 215
2015-02-24
Request user confirmation | There is no option to implement these actions in View.
Get all comment notifications
Unlike post
Update comment
unfollow
unfriend
cancel share
2015-02-25
FragmentProfile | It is second time! Don't display "null" when the user's aboutMe is NULL | as I said I think it should be handled in webserver or webservice controls, view handles anything be received
FragmentSearchUser | User shouldn't be able to search user with Persian language
After you choose one of the history list's items, the list will not disapear and the selected item will remain in the list. You should display all items so user can select another item or do not display any item after choosing one item. I think frist suggestion is more reasonable.
FagmentResultUser | Don't display blank page when search result is empty. Display a message.
By clicking on serach result item, the GetUserHomeInfo will not call! What do you call?!!
What is the delete icon in search result listview?
FragmentMap | If it is first time user see this page, display a message with this conten: برای انتخاب محل کسب و کار خود، بر روی یک نقطه از نقشه کلیک نمایید
ActivityNewBusienss_step2 | check inputed website address to match website format
check inputed phone number to match phone number format (a value with 7 or 8 digits)
| check inputed cellphone number to match cellphone number format( starts with "09" and 11 digits limitation | my decision was :: It's text, so it can contain 2 numbers with different formats for example, we can't limit user
ActivitySetting | After successful implementation and displaying dialog, by clicking on the dialog button: Force Close
FragmentProfile | Don't display search icon in business home info
FragmentCallInfo | It is the second time! Display map with reasonable zoom scale so that the user can see highways and main street's name
display hashtags in appropriate way, like : "#ساعت#,فروش
hashtags must be clickable and open search page with the hashtag's value after clicking on a hashtag
| There is no webservice to get business' contact info. I forgat that but you implemented the page and you saw you don't have: email website phone number cellphone number how did not infrom me?!!!! | we have these data in business class
Implement getResult and getError
ActivityNewPost_step2 | It is the second time! getResult: force close
Post page (reachable by clicking on gridview) | display business user name instead of static name
PostAdapter | change default picture for the post
hashtags must be clickable and therefore open search page with the hashtag's value after clicking on a hashtag

## Kaveh
unComment option.java
implement AccessToken
Talk with Mr. Hos about sharing post in instagram
implement Google Analytic
Check camera speed

## App
Should not be displayed TimeLine page with no posts. It shouldn't be blank